Lending - Approval to Funding

Quarterly Business Review Memo

| Q3 FY26 | Domain Lead: Cameron Sucharda |
| --- | --- |
| Date: April 15, 2026 |  |

[Domain name]: Reduce friction and improve conversion from approval to funding while increasing customer self-service.

1.1	Executive summary:

| The key priority for last quarter was to focus … | The key priority for last quarter was to focus on reduce friction across the approval-to-funding journey, with deliberate focus on three areas: simplifying document submission, removing manual review bottlenecks to reduce cycle time, and expanding digital self-service to reduce assisted support demand. Effort was concentrated on the highest drop-off moments in the journey -- particularly document-related friction between approval and funding -- where customer confusion and redundant process steps were suppressing conversion.. |
| --- | --- |
| Key learnings this quarter were | - Clarity, not speed, drives customer behavior. Removing redundant document requests and providing clearer instructions had a disproportionately large impact on both conversion (+3 pts) and NPS (+1.5 pts). The primary mechanism was reduced customer uncertainty -- not process acceleration. This challenges the assumption that cycle time is the primary lever for funding conversion. - Reducing friction in a small number of high-impact moments delivers outsized gains. Focused changes at the document submission stage drove improvements across funding rate, drop-off, and experience simultaneously -- confirming the approval-to-funding journey is won or lost at discrete friction points, not across the whole flow. - Automation alone does not solve for complexity. Partial automation of manual review reduced queue volume by ~15%, but complex cases still required full manual intervention. The structural constraint is case variability, not automation maturity -- a distinction that should shape Q2 investment in early validation rather than further queue automation. - Proactive visibility reduces support demand. Introducing proactive status tracking and clearer next steps drove a 10% reduction in call volume alongside a 7-point improvement in self-service rate -- confirming that customers escalate when uncertain, not merely when dissatisfied. |
| Our next opportunities are | - Scale document simplification to more complex customer scenarios, where drop-off and friction remain highest and Q1 gains have not yet reached. - Further reduce approval-to-funding cycle time from 18.5 to ~18 days by expanding early validation and straight-through processing for standard cases. - Extend self-service capability to edge cases and non-standard journeys, which currently fall back to assisted support and represent the next frontier of call volume reduction. |

1.2	Objectives and Key Results (OKRs)

Aim for 3 Objectives with 3-5 Key Results per Objective. Include a mix of leading action and lagging results in the Key Results.

| Upstream Domain Linkage | Objectives | Key Results | Status | Support needed |
| --- | --- | --- | --- | --- |
| Supports PBB OKR to increase digital engagement and reduce assisted service cost. This OKR addresses the primary conversion gap between approval and funding by eliminating friction at the moments customers most commonly disengage. | Shift customers to active owners of their funding journey through friction elimination. | Increase funding conversion rate from 65% to 68% | 65% (Q1 baseline; up from 62% in Q0) |  |
|  |  | Reduce document-related drop-off from 12% to less than 10% | 12% (down from 18% in Q0) | Alignment with Upstream Approval and Credit Crews to reduce redundant upstream document requirements |
|  |  | Enable 70% of customers to complete document submission without assisted support | Baseline being established in Q2 | Digital Channels for consistent action and guidance presentation |
| Supports PBB operational efficiency OKR. This OKR exists to reduce manual handling cost and cycle time, enabling higher throughput without proportional resource growth. | Build a faster, more automated operational backbone for the funding journey. | Reduce approval-to-funding cycle time from 18.5 to 18 days | 18.5 days (down from 19 days in Q0) |  |
|  |  | Reduce manual review volume by an additional 20% | -15% achieved in Q1; further reduction targeted | Enterprise Credit to approve early-stage validation rules and tolerance thresholds for complex cases |
|  |  | Increase straight-through processing for standard cases to 75% | Baseline being established in Q2 | Credit and Technology teams to enable automated early validation |
| Supports PBB digital engagement and customer experience OKRs. This OKR scales Q1 self-service gains to a broader range of customer scenarios, reducing structural dependency on assisted channels. | Make digital self-service the default across the approval-to-funding journey. | Increase self-service rate from 65% to 72% | 65% (up from 58% in Q0) |  |
|  |  | Reduce inbound call volume by an additional 10% on top of Q1 reduction | -10% achieved in Q1; further reduction targeted | Cross-domain alignment on consistent status messaging and next-step guidance |
|  |  | Improve NPS by +2 pts over Q1 baseline | +1.5 pts in Q1; trajectory positive |  |

1.3 KPIs & Financials dashboard

Provide a focused set of ongoing KPIs that reflect steady-state business health. KPIs should cover a mix of client outcomes, operational performance, people, and financial impact. Do not use KPIs to track one-off initiatives or strategic change

| Dashboard |  | Q3 |  |  | Q4 | FY26 |  | Upstream KPI Impact |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Actual |  | Target | Target | Actuals to Date | Year End |  |
| Client Outcomes | Funding conversion rate | 65% | ● | 68% | 70% | 65% | 70% | PBB Total client growth |
|  | Document drop-off rate | 12% | ● | <10% | <8% | 12% | <8% |  |
|  | Digital self-service rate | 65% | ● | 72% | 75% | 65% | 75% | PBB digital engagement rate |
| Operational Performance | Approval-to-funding cycle time | 18.5 days | ● | 18.0 days | 17.5 days | 18.5 days | 17.5 days | PBB operational efficiency |
|  | Manual review volume (vs. baseline) | -15% | ● | -35% cumulative | -40% cumulative | -15% | -40% cumulative |  |
| People | To be confirmed |  | ● |  |  |  |  |  |
| Financial Impact | Inbound call volume reduction (vs. baseline) | -10% | ● | -20% cumulative | -30% cumulative | -10% | -30% cumulative | Assisted service cost |
|  | NPS (cumulative improvement) | +1.5 pts | ● | +3 pts | +5 pts | +1.5 pts | +5 pts | PBB NPS |

1.4	Key Issues & Dependencies

Outline the items that are dependent on other items being prioritised external to the Domain. To be populated from JIRA. Should only include Dependencies that require escalation.

| Tracking # & Type | Constraint or Dependency | Required Action and Accountable Owner(s) | Decision or Resolution Needed By |
| --- | --- | --- | --- |
| Jira: 12345 | Early LTV and document validation services for approval-to-funding journey | Enterprise Credit to approve early-stage validation rules and tolerance thresholds | September |

1.5	Risks

Outline the items that are risks or blockers that require solving by PBB ELT & Partners. Should only include Risks that require escalation.

| Risks/ Blockers | Asks for PBB ELT & Partners |
| --- | --- |
| "Funding-ready" lacks a consistent, shared definition across teams and channels, leading to inconsistent customer guidance, cautious decision-making, and duplicated indicators that create confusion rather than clarity. If unresolved, this will limit the impact of self-service improvements and create quality risk as we scale. | Endorse a single, authoritative definition of "funding-ready" as the primary decision point across all channels and teams. Support consistent application of this definition, including retiring familiar but duplicative indicators where they conflict. |
| Improvement gains risk plateauing if edge cases are not addressed as a deliberate priority. Q1 wins were concentrated in standard journeys. Edge cases -- which carry higher manual effort, longer cycle time, and higher drop-off -- are not yet within scope of existing initiatives and will become the binding constraint on further conversion and NPS improvement. | Align on prioritising end-to-end journey optimisation over siloed, within-team efficiency gains. Direct relevant domains (Credit, Approval, Digital) to treat edge-case resolution as a shared, cross-domain objective rather than a secondary backlog item. |

Appendix

Appendix: Q3 Initiatives

Each Domain should identify the initiatives (Aim for 3, depending on size) that they will be working on in the coming quarter.

| Initiative ID | Crews | Initiative | Outcomes to be provided | Relevant OKRs | Confidence (H/M/L) | Key risks/ Dependencies |
| --- | --- | --- | --- | --- | --- | --- |
| 1 TBC | Lending Ops | Document Simplification Expansion | Reduced drop-off and improved conversion | O1: Improve funding conversion through friction reduction | High | Dependency on upstream Approval and Credit |